## Final
Start date | 2026-02-16 |  |  |  | Display type | Weekly
TRG GHS Project Gantt Chart |  |  |  |  | Display period | 1
|  |  | Legend bars | Phase Overhead task Subtask Subtask Milestone | time axis 2026-02-16 to 2027-11-12
End date | 2027-10-08 | time axis 2026-02-16 to 2027-11-12
[7 empty] | Week |  |  |  | 2026-02-16: 1; 2026-02-23: 2; 2026-03-02: 3; 2026-03-09: 4; 2026-03-16: 5; 2026-03-23: 6; 2026-03-30: 7; 2026-04-07: 8; 2026-04-13: 9; 2026-04-20: 10; 2026-04-27: 11; 2026-05-04: 12; 2026-05-11: 13; 2026-05-18: 14; 2026-05-25: 15; 2026-06-01: 16; 2026-06-09: 17; 2026-06-15: 18; 2026-06-22: 19; 2026-06-29: 20; 2026-07-06: 21; 2026-07-13: 22; 2026-07-20: 23; 2026-07-27: 24; 2026-08-03: 25; 2026-08-10: 26; 2026-08-17: 27; 2026-08-24: 28; 2026-08-31: 29; 2026-09-07: 30; 2026-09-14: 31; 2026-09-21: 32; 2026-09-28: 33; 2026-10-06: 34; 2026-10-12: 35; 2026-10-19: 36; 2026-10-26: 37; 2026-11-02: 38; 2026-11-09: 39; 2026-11-16: 40; 2026-11-23: 41; 2026-11-30: 42; 2026-12-07: 43; 2026-12-14: 44; 2026-12-21: 45; 2026-12-29: 46; 2027-01-04: 47; 2027-01-11: 48; 2027-01-18: 49; 2027-01-25: 50; 2027-02-01: 51; 2027-02-08: 52; 2027-02-15: 53; 2027-02-22: 54; 2027-03-01: 55; 2027-03-08: 56; 2027-03-15: 57; 2027-03-22: 58; 2027-03-30: 59; 2027-04-05: 60; 2027-04-12: 61; 2027-04-19: 62; 2027-04-26: 63; 2027-05-03: 64; 2027-05-10: 65; 2027-05-17: 66; 2027-05-24: 67; 2027-05-31: 68; 2027-06-07: 69; 2027-06-15: 70; 2027-06-21: 71; 2027-06-28: 72; 2027-07-05: 73; 2027-07-12: 74; 2027-07-19: 75; 2027-07-26: 76; 2027-08-02: 77; 2027-08-09: 78; 2027-08-16: 79; 2027-08-23: 80; 2027-08-30: 81; 2027-09-06: 82; 2027-09-13: 83; 2027-09-20: 84; 2027-09-27: 85; 2027-10-05: 86
WBS (Task ID) | Description | Colour | Duration (days) | Start | End | Predecessor | Successor | Network days | Critical | Cal days
0.0 | TRG GHS Project | [6 empty] | - |  | 0
1.0 | Project Initiation | O | 20 | 2026-02-16 | 2026-03-13 | - | 1.1 | 20 | 0 | 25
1.1 | Develop Project Charter | P | 10 | 2026-02-16 | 2026-02-27 | 1.0 | 1.1.1 | 10 | 0 | 11
1.1.1 | Define project purpose | R | 2 | 2026-02-16 | 2026-02-17 | 1.1 | 1.1.2 | 2 | 0 | 1
1.1.2 | Define measurable objectives (MOV) | R | 2 | 2026-02-18 | 2026-02-19 | 1.1.1 | 1.1.3 | 2 | 0 | 1
1.1.3 | Define high-level scope | R | 3 | 2026-02-20 | 2026-02-24 | 1.1.2 | 1.1.4 | 3 | 0 | 4
1.1.4 | Identify success criteria | R | 3 | 2026-02-25 | 2026-02-27 | 1.1.3 | 1.2 | 3 | 0 | 2
1.2 | Identify stakeholders | P | 6 | 2026-03-02 | 2026-03-09 | 1.1.4 | 1.2.1, 1.2.2 | 6 | 0 | 7
1.2.1 | List internal stakeholders | R | 2 | 2026-03-02 | 2026-03-03 | 1.2 | 1.2.3 | 2 | 0 | 1
1.2.2 | List external stakeholders | R | 2 | 2026-03-02 | 2026-03-03 | 1.2 | 1.2.3 | 2 | 0 | 1
1.2.3 | Assess stakeholder influence and interest | R | 2 | 2026-03-04 | 2026-03-05 | 1.2.1, 1.2.2 | 1.2.4 | 2 | 0 | 1
1.2.4 | Document stakeholder roles and responsibilities | R | 2 | 2026-03-06 | 2026-03-09 | 1.2.3 | 1.3 | 2 | 0 | 3
1.3 | Obtain Sponsor Approval to Begin Planning | P | 4 | 2026-03-10 | 2026-03-13 | 1.2.4 | 1.4 | 4 | 0 | 3
1.4 | Milestone: Project Initiated | M | 0 | 2026-03-13 | 2026-03-13 | 1.3 | 2.0 | 0 | 0 | 0
2.0 | Project Planning | O | 48 | 2026-03-16 | 2026-05-22 | 1.4 | 2.1 | 48 | 0 | 67
2.1 | Create Work Breakdown Structure (WBS) | P | 7 | 2026-03-16 | 2026-03-24 | 2.0 | 2.1.1 | 7 | 0 | 8
2.1.1 | Divide project into major deliverables | R | 3 | 2026-03-16 | 2026-03-18 | 2.1 | 2.1.2 | 3 | 0 | 2
2.1.2 | Submit WBS to project sponsor | R | 2 | 2026-03-19 | 2026-03-20 | 2.1.1 | 2.1.3 | 2 | 0 | 1
2.1.3 | Complete WBS | R | 2 | 2026-03-23 | 2026-03-24 | 2.1.2 | 2.2 | 2 | 0 | 1
2.2 | Develop Project Schedule | P | 6 | 2026-03-25 | 2026-04-01 | 2.1.3 | 2.2.1, 2.2.2 | 6 | 0 | 7
2.2.1 | Create Gantt chart | R | 6 | 2026-03-25 | 2026-04-01 | 2.2 | 2.3 | 6 | 0 | 7
2.2.2 | Create network diagrams | R | 4 | 2026-03-25 | 2026-03-30 | 2.2 | 2.3 | 4 |  | 5
2.3 | Prepare Project Budget | P | 14 | 2026-04-02 | 2026-04-23 | 2.2.1, 2.2.2 | 2.3.1 | 14 | 0 | 21
2.3.1 | Develop resource-loaded schedule | R | 4 | 2026-04-02 | 2026-04-09 | 2.3 | 2.3.2 | 4 | 0 | 7
2.3.2 | Conduct bottom-up estimation | R | 4 | 2026-04-10 | 2026-04-15 | 2.3.1 | 2.3.3 | 4 | 0 | 5
2.3.3 | Add indirect costs and summarise budget | R | 4 | 2026-04-16 | 2026-04-21 | 2.3.2 | 2.3.4 | 4 | 0 | 5
2.3.4 | Finalise Budget as "Cost Baseline" | R | 2 | 2026-04-22 | 2026-04-23 | 2.3.3 | 2.4 | 2 | 0 | 1
2.4 | Define Change Control Methodology | P | 2 | 2026-04-24 | 2026-04-27 | 2.3.4 | 2.5 | 2 | 0 | 3
2.5 | Define Constraints, Assumptions and Risks | P | 4 | 2026-04-28 | 2026-05-01 | 2.4 | 2.6 | 4 | 0 | 3
2.6 | Create Risk Management Plan | P | 2 | 2026-05-04 | 2026-05-05 | 2.5 | 2.7 | 2 | 0 | 1
2.7 | Develop Communications Plan | P | 4 | 2026-05-06 | 2026-05-11 | 2.6 | 2.8 | 4 | 0 | 5
2.8 | Develop Quality Management Plan | P | 6 | 2026-05-12 | 2026-05-19 | 2.7 | 2.8.1, 2.8.2 | 6 | 0 | 7
2.8.1 | Define Quality Objectives | R | 4 | 2026-05-12 | 2026-05-15 | 2.8 | 2.9 | 4 |  | 3
2.8.2 | Identify Quality Metrics | R | 6 | 2026-05-12 | 2026-05-19 | 2.8 | 2.9 | 6 | 0 | 7
2.9 | Develop Procurement Plan | P | 3 | 2026-05-20 | 2026-05-22 | 2.8.1, 2.8.2 | 2.10 | 3 | 0 | 2
2.10 | Milestone: Project Plan Approved | M | 0 | 2026-05-22 | 2026-05-22 | 2.9 | 3.0 | 0 | 0 | 0
3.0 | Requirements Analysis | O | 22 | 2026-05-25 | 2026-06-24 | 2.10 | 3.1 | 22 | 0 | 30
3.1 | Define Functional Requirements | P | 8 | 2026-05-25 | 2026-06-03 | 3.0 | 3.1.1, 3.1.3, 3.1.4, 3.1.5 | 8 | 0 | 9
3.1.1 | Identify booking module requirements | R | 4 | 2026-05-25 | 2026-05-28 | 3.1 | 3.1.2 | 4 | 0 | 3
3.1.2 | Identify payment module requirements | R | 4 | 2026-05-29 | 2026-06-03 | 3.1.1 | 3.2 | 4 | 0 | 5
3.1.3 | Identify CRM requirements | R | 4 | 2026-05-25 | 2026-05-28 | 3.1 | 3.2 | 4 |  | 3
3.1.4 | Identify event and activity requirements | R | 4 | 2026-05-25 | 2026-05-28 | 3.1 | 3.2 | 4 |  | 3
3.1.5 | Identify e-store requirements | R | 4 | 2026-05-25 | 2026-05-28 | 3.1 | 3.2 | 4 |  | 3
3.2 | Define Non-Functional Requirements | P | 5 | 2026-06-04 | 2026-06-11 | 3.1.2 , 3.1.3, 3.1.4, 3.1.5 | 3.3 | 5 | 0 | 7
3.3 | Document User Stories | P | 4 | 2026-06-12 | 2026-06-17 | 3.2 | 3.3.1, 3.3.2 | 4 | 0 | 5
3.3.1 | Write staff user stories | R | 2 | 2026-06-12 | 2026-06-15 | 3.3 | 3.3.3 | 2 | 0 | 3
3.3.2 | Write guest user stories | R | 2 | 2026-06-12 | 2026-06-15 | 3.3 | 3.3.3 | 2 | 0 | 3
3.3.3 | Validate User Stories With Stakeholders | R | 2 | 2026-06-16 | 2026-06-17 | 3.3.1, 3.3.2 | 3.4 | 2 | 0 | 1
3.4 | Conduct Compliance Requirement Analysis | P | 5 | 2026-06-18 | 2026-06-24 | 3.3.3 | 3.4.1, 3.4.2 | 5 | 0 | 6
3.4.1 | Check ACSC Essential Eight Requirements | R | 2 | 2026-06-18 | 2026-06-19 | 3.4 | 3.4.3 | 2 | 0 | 1
3.4.2 | Check Privacy Act 1988 requirements | R | 2 | 2026-06-18 | 2026-06-19 | 3.4 | 3.4.3 | 2 | 0 | 1
3.4.3 | Consolidate Compliance Report | R | 3 | 2026-06-22 | 2026-06-24 | 3.4.1, 3.4.2 | 3.5 | 3 | 0 | 2
3.5 | Milestone: Requirements Approved | M | 0 | 2026-06-24 | 2026-06-24 | 3.4.3 | 4.0 | 0 | 0 | 0
4.0 | System design | O | 21 | 2026-06-25 | 2026-07-23 | 3.5 | 4.1 | 21 | 0 | 28
4.1 | Design System Architecture | P | 3 | 2026-06-25 | 2026-06-29 | 4.0 | 4.1.1, 4.1.2, 4.1.3 | 3 | 0 | 4
4.1.1 | Define server requirements | R | 3 | 2026-06-25 | 2026-06-29 | 4.1 | 4.2 , 4.3 , 4.4 | 3 | 0 | 4
4.1.2 | Define database design | R | 3 | 2026-06-25 | 2026-06-29 | 4.1 | 4.2 , 4.3 , 4.4 | 3 | 0 | 4
4.1.3 | Define API structure | R | 3 | 2026-06-25 | 2026-06-29 | 4.1 | 4.2 , 4.3 , 4.4 | 3 | 0 | 4
4.2 | Design Booking and Payment Modules | P | 7 | 2026-06-30 | 2026-07-08 | 4.1.1, 4.1.2, 4.1.3 | 4.2.1, 4.2.2 | 7 | 0 | 8
4.2.1 | Create booking UI wireframes | R | 4 | 2026-06-30 | 2026-07-03 | 4.2 | 4.2.3 | 4 | 0 | 3
4.2.2 | Create payment gateway workflows | R | 4 | 2026-06-30 | 2026-07-03 | 4.2 | 4.2.3 | 4 | 0 | 3
4.2.3 | Review Booking and Payment Designs | R | 3 | 2026-07-06 | 2026-07-08 | 4.2.1, 4.2.2 | 4.5 | 3 | 0 | 2
4.3 | Design Event and Activity Modules | P | 7 | 2026-06-30 | 2026-07-08 | 4.1.1, 4.1.2, 4.1.3 | 4.3.1, 4.3.2 | 7 | 0 | 8
4.3.1 | Create event booking workflows | R | 4 | 2026-06-30 | 2026-07-03 | 4.3 | 4.3.3 | 4 | 0 | 3
4.3.2 | Create childcare and lesson workflows | R | 4 | 2026-06-30 | 2026-07-03 | 4.3 | 4.3.3 | 4 | 0 | 3
4.3.3 | Review Event Module Designs | R | 3 | 2026-07-06 | 2026-07-08 | 4.3.1, 4.3.2 | 4.5 | 3 | 0 | 2
4.4 | Design Merchandise E-Store | P | 4 | 2026-06-30 | 2026-07-03 | 4.1.1, 4.1.2, 4.1.3 | 4.4.1, 4.4.2 | 4 |  | 3
4.4.1 | Create product catalogue | R | 4 | 2026-06-30 | 2026-07-03 | 4.4 | 4.5 | 4 |  | 3
4.4.2 | Create checkout workflow | R | 4 | 2026-06-30 | 2026-07-03 | 4.4 | 4.5 | 4 |  | 3
4.5 | Design Data Security and Backup Processes | P | 11 | 2026-07-09 | 2026-07-23 | 4.2.3, 4.3.3, 4.4.1, 4.4.2 | 4.5.1, 4.5.2 | 11 | 0 | 14
4.5.1 | Define encryption methods | R | 4 | 2026-07-09 | 2026-07-14 | 4.5 | 4.5.3 | 4 | 0 | 5
4.5.2 | Define access control model | R | 3 | 2026-07-09 | 2026-07-13 | 4.5 | 4.5.3 | 3 |  | 4
4.5.3 | Define backup process | R | 3 | 2026-07-15 | 2026-07-17 | 4.5.1, 4.5.2 | 4.5.4 | 3 | 0 | 2
4.5.4 | Peer Review of Design Documents | R | 4 | 2026-07-20 | 2026-07-23 | 4.5.3 | 4.6 | 4 | 0 | 3
4.6 | Milestone: System Design Complete | M | 0 | 2026-07-23 | 2026-07-23 | 4.5.4 | 5.0 | 0 | 0 | 0
5.0 | Development / Coding | O | 75 | 2026-07-24 | 2026-11-06 | 4.6 | 5.1 , 5.2 , 5.4 | 75 | 0 | 105
5.1 | Develop Booking and Payment Module | P | 11 | 2026-07-24 | 2026-08-07 | 5.0 | 5.1.1, 5.1.2 | 11 | 0 | 14
5.1.1 | Code booking module UI | R | 4 | 2026-07-24 | 2026-07-29 | 5.1 | 5.1.3 | 4 | 0 | 5
5.1.2 | Implement booking backend logic | R | 4 | 2026-07-24 | 2026-07-29 | 5.1 | 5.1.3 | 4 | 0 | 5
5.1.3 | Integrate Payment Gateways | R | 5 | 2026-07-30 | 2026-08-05 | 5.1.1, 5.1.2 | 5.1.4, 5.2.3 | 5 | 0 | 6
5.1.4 | Unit Test Payment and Booking | R | 2 | 2026-08-06 | 2026-08-07 | 5.1.3 | 5.2.4 | 2 |  | 1
5.2 | Develop Guest Information Management (CRM) | P | 10 | 2026-07-24 | 2026-08-13 | 5.0 | 5.2.1, 5.2.2 | 15 |  | 20
5.2.1 | Code CRM UI | R | 4 | 2026-07-24 | 2026-07-29 | 5.2 | 5.2.3 | 4 |  | 5
5.2.2 | Code CRM backend logic | R | 4 | 2026-07-24 | 2026-07-29 | 5.2 | 5.2.3 | 4 |  | 5
5.2.3 | Implement user account managment | R | 4 | 2026-08-06 | 2026-08-11 | 5.1.3, 5.2.1, 5.2.2 | 5.2.4, 5.4.2 | 4 | 0 | 5
5.2.4 | Unit Test CRM Module | R | 2 | 2026-08-12 | 2026-08-13 | 5.1.4, 5.2.3 | 5.3 , 5.4.3 | 2 | 0 | 1
5.3 | Develop Activity Registration Portal | P | 12 | 2026-08-14 | 2026-08-31 | 5.2.4 | 5.3.1, 5.3.2 | 12 | 0 | 17
5.3.1 | Code activity registration UI | R | 4 | 2026-08-14 | 2026-08-19 | 5.3 | 5.3.3 | 4 | 0 | 5
5.3.2 | Code activity backend logic | R | 4 | 2026-08-14 | 2026-08-19 | 5.3 | 5.3.3 | 4 | 0 | 5
5.3.3 | Integration Activity Module with CRM | R | 6 | 2026-08-20 | 2026-08-27 | 5.3.1, 5.3.2 | 5.3.4, 5.5 | 6 | 0 | 7
5.3.4 | Unit Test Activity Portal | R | 2 | 2026-08-28 | 2026-08-31 | 5.3.3 | 5.5.2 | 2 | 0 | 3
5.4 | Develop Merchandise E-Store | P | 10 | 2026-07-24 | 2026-08-19 | 5.0 | 5.4.1 | 19 |  | 26
5.4.1 | Build product catalogue | R | 4 | 2026-07-24 | 2026-07-29 | 5.4 | 5.4.2 | 4 |  | 5
5.4.2 | Build cart and checkout system | R | 4 | 2026-08-12 | 2026-08-17 | 5.2.3, 5.4.1 | 5.4.3 | 4 |  | 5
5.4.3 | Unit Test E-Store Module | R | 2 | 2026-08-18 | 2026-08-19 | 5.2.4, 5.4.2 | 5.6 | 2 |  | 1
5.5 | Develop Sponsorship and Competition | P | 6 | 2026-08-28 | 2026-09-08 | 5.3.3 | 5.5.1, 5.5.2 | 8 |  | 11
5.5.1 | Develop sponsor registration | R | 4 | 2026-08-28 | 2026-09-02 | 5.5 | 5.5.3 | 4 |  | 5
5.5.2 | Develop competition registration | R | 4 | 2026-09-01 | 2026-09-04 | 5.3.4, 5.5 | 5.5.3 | 4 | 0 | 3
5.5.3 | Unit Test Sponsorship and Competition Module | R | 2 | 2026-09-07 | 2026-09-08 | 5.5.1, 5.5.2 | 5.6 | 2 | 0 | 1
5.6 | Build Security and Compliance Framework | P | 9 | 2026-09-09 | 2026-09-21 | 5.4.3, 5.5.3 | 5.6.1, 5.6.2 | 9 | 0 | 12
5.6.1 | Implement encryption | R | 5 | 2026-09-09 | 2026-09-15 | 5.6 | 5.6.3 | 5 | 0 | 6
5.6.2 | Implement access controls | R | 4 | 2026-09-09 | 2026-09-14 | 5.6 | 5.6.3 | 4 |  | 5
5.6.3 | Implement data backup | R | 4 | 2026-09-16 | 2026-09-21 | 5.6.1, 5.6.2 | 5.7 | 4 | 0 | 5
5.7 | Develop Integration APIs | P | 13 | 2026-09-22 | 2026-10-09 | 5.6.3 | 5.7.1, 5.7.2 | 13 | 0 | 17
5.7.1 | Implement API for booking system | R | 6 | 2026-09-22 | 2026-09-29 | 5.7 | 5.7.3 | 6 | 0 | 7
5.7.2 | Implement for payment system | R | 6 | 2026-09-22 | 2026-09-29 | 5.7 | 5.7.3 | 6 | 0 | 7
5.7.3 | Implement API for third-party systems (e.g. booking.com) | R | 7 | 2026-09-30 | 2026-10-09 | 5.7.1, 5.7.2 | 5.8 | 7 | 0 | 9
5.8 | Code Review and Refactoring | P | 20 | 2026-10-12 | 2026-11-06 | 5.7.3 | 5.8.1 | 20 | 0 | 25
5.8.1 | Code Review of Design Documents | R | 15 | 2026-10-12 | 2026-10-30 | 5.8 | 5.8.2 | 15 | 0 | 18
5.8.2 | Compliance Benchmark Check (ACSC/Privacy Act) | R | 5 | 2026-11-02 | 2026-11-06 | 5.8.1 | 5.9 | 5 | 0 | 4
5.9 | Milestone: Prototype Complete | M | 0 | 2026-11-06 | 2026-11-06 | 5.8.2 | 6.0 | 0 | 0 | 0
6.0 | Testing | O | 75 | 2026-11-09 | 2027-02-25 | 5.9 | 6.1 | 75 | 0 | 108
6.1 | Develop Test Plan and Cases | P | 23 | 2026-11-09 | 2026-12-09 | 6.0 | 6.1.1 | 23 | 0 | 30
6.1.1 | Define functional test cases | R | 6 | 2026-11-09 | 2026-11-16 | 6.1 | 6.1.2 | 6 | 0 | 7
6.1.2 | Define non-functional test cases | R | 6 | 2026-11-17 | 2026-11-24 | 6.1.1 | 6.1.3 | 6 | 0 | 7
6.1.3 | Define integration test cases | R | 6 | 2026-11-25 | 2026-12-02 | 6.1.2 | 6.1.4 | 6 | 0 | 7
6.1.4 | Review test plan with stakeholders | R | 5 | 2026-12-03 | 2026-12-09 | 6.1.3 | 6.2 | 5 | 0 | 6
6.2 | Report Test Results | P | 32 | 2026-12-10 | 2027-01-28 | 6.1.4 | 6.2.1 | 32 | 0 | 49
6.2.1 | Conduct system testing | R | 7 | 2026-12-10 | 2026-12-18 | 6.2 | 6.2.1.1, 6.2.1.2, 6.2.1.3 | 7 | 0 | 8
6.2.1.1 | Execute functional tests | G | 4 | 2026-12-10 | 2026-12-15 | 6.2.1 | 6.2.1.4 | 4 |  | 5
6.2.1.2 | Execute non-functional tests | G | 5 | 2026-12-10 | 2026-12-16 | 6.2.1 | 6.2.1.4 | 5 | 0 | 6
6.2.1.3 | Execute integration tests | G | 4 | 2026-12-10 | 2026-12-15 | 6.2.1 | 6.2.1.4 | 4 |  | 5
6.2.1.4 | Document test results | G | 2 | 2026-12-17 | 2026-12-18 | 6.2.1.1, 6.2.1.2, 6.2.1.3 | 6.2.2 | 2 | 0 | 1
6.2.2 | Analyze results | R | 17 | 2026-12-21 | 2027-01-15 | 6.2.1.4 | 6.2.2.1 | 17 | 0 | 25
6.2.2.1 | Identify software issues | G | 2 | 2026-12-21 | 2026-12-22 | 6.2.2 | 6.2.2.2 | 2 | 0 | 1
6.2.2.2 | Execute Quality Inspections on Test Results | G | 3 | 2026-12-23 | 2026-12-29 | 6.2.2.1 | 6.2.2.3 | 3 | 0 | 6
6.2.2.3 | Review Test Coverage and Pass Rate | G | 2 | 2026-12-30 | 2026-12-31 | 6.2.2.2 | 6.2.2.4 | 2 | 0 | 1
6.2.2.4 | Review results with stakeholder | G | 4 | 2027-01-04 | 2027-01-07 | 6.2.2.3 | 6.2.2.5 | 4 | 0 | 3
6.2.2.5 | Fix identified issues | G | 6 | 2027-01-08 | 2027-01-15 | 6.2.2.4 | 6.2.3 | 6 | 0 | 7
6.2.3 | Prepare test results report and presentation | R | 4 | 2027-01-18 | 2027-01-21 | 6.2.2.5 | 6.2.4 | 4 | 0 | 3
6.2.4 | Present test results to TRG | R | 2 | 2027-01-22 | 2027-01-25 | 6.2.3 | 6.2.5 | 2 | 0 | 3
6.2.5 | TRG Sign-off Test Results | R | 2 | 2027-01-27 | 2027-01-28 | 6.2.4 | 6.3 | 2 | 0 | 1
6.3 | Conduct User Acceptance Testing (UAT) | P | 20 | 2027-01-29 | 2027-02-25 | 6.2.5 | 6.3.1 | 20 | 0 | 27
6.3.1 | Prepare UAT scripts | R | 7 | 2027-01-29 | 2027-02-08 | 6.3 | 6.3.2 | 7 | 0 | 10
6.3.2 | Run UAT sessions with TRG staff | R | 5 | 2027-02-09 | 2027-02-15 | 6.3.1 | 6.3.3 | 5 | 0 | 6
6.3.3 | Apply fixes from UAT feedback | R | 6 | 2027-02-16 | 2027-02-23 | 6.3.2 | 6.3.4 | 6 | 0 | 7
6.3.4 | UAT Sign-Off | R | 2 | 2027-02-24 | 2027-02-25 | 6.3.3 | 6.4 | 2 | 0 | 1
6.4 | Milestone: Testing Complete | M | 0 | 2027-02-25 | 2027-02-25 | 6.3.4 | 7.0 | 0 | 0 | 0
7.0 | Deployment | O | 98 | 2027-02-26 | 2027-07-16 | 6.4 | 7.1 | 98 | 0 | 140
7.1 | Develop Deployment Plan | P | 30 | 2027-02-26 | 2027-04-12 | 7.0 | 7.1.1 | 30 | 0 | 45
7.1.1 | Draft rollout plan | R | 8 | 2027-02-26 | 2027-03-09 | 7.1 | 7.1.2 | 8 | 0 | 11
7.1.2 | Define go-live criteria | R | 6 | 2027-03-10 | 2027-03-17 | 7.1.1 | 7.1.3 | 6 | 0 | 7
7.1.3 | Define data migration steps | R | 5 | 2027-03-18 | 2027-03-24 | 7.1.2 | 7.1.4 | 5 | 0 | 6
7.1.4 | Define rollback and contingency plan | R | 7 | 2027-03-25 | 2027-04-06 | 7.1.3 | 7.1.5 | 7 | 0 | 12
7.1.5 | Review Deployment Plan with Stakeholders | R | 4 | 2027-04-07 | 2027-04-12 | 7.1.4 | 7.2 , 7.3 | 4 | 0 | 5
7.2 | Integrate with Legacy Systems and Prepare Environment | P | 33 | 2027-04-13 | 2027-05-27 | 7.1.5 | 7.2.1 | 33 |  | 44
7.2.1 | Identify legacy systems for integration | R | 3 | 2027-04-13 | 2027-04-15 | 7.2 | 7.2.2 | 3 |  | 2
7.2.2 | Map data flows between systems | R | 6 | 2027-04-16 | 2027-04-23 | 7.2.1 | 7.2.3, 7.2.4 | 6 |  | 7
7.2.3 | Configure servers and databases | R | 8 | 2027-04-26 | 2027-05-05 | 7.2.2 | 7.2.5 | 8 |  | 9
7.2.4 | Configure APIs and integration | R | 5 | 2027-04-26 | 2027-04-30 | 7.2.2 | 7.2.5 | 5 |  | 4
7.2.5 | Perform security hardening | R | 8 | 2027-05-06 | 2027-05-17 | 7.2.3, 7.2.4 | 7.2.6 | 8 |  | 11
7.2.6 | Execute legacy system integration | R | 8 | 2027-05-18 | 2027-05-27 | 7.2.5 | 7.4.5 | 8 |  | 9
7.3 | Train TRG Staff and End Users | P | 25 | 2027-04-13 | 2027-05-17 | 7.1.5 | 7.3.1 | 25 | 0 | 34
7.3.1 | Create training materials | R | 6 | 2027-04-13 | 2027-04-20 | 7.3 | 7.3.2 | 6 | 0 | 7
7.3.2 | Conduct training sessions | R | 8 | 2027-04-21 | 2027-04-30 | 7.3.1 | 7.3.3, 7.3.5 | 8 | 0 | 9
7.3.3 | Collect training feedback | R | 5 | 2027-05-03 | 2027-05-07 | 7.3.2 | 7.3.4 | 5 | 0 | 4
7.3.4 | Adjust training based on feedback | R | 5 | 2027-05-10 | 2027-05-14 | 7.3.3 | 7.3.6 | 5 | 0 | 4
7.3.5 | Conduct knowledge transfer workshops | R | 6 | 2027-05-03 | 2027-05-10 | 7.3.2 | 7.3.6 | 6 |  | 7
7.3.6 | Complete Training | R | 1 | 2027-05-17 | 2027-05-17 | 7.3.4, 7.3.5 | 7.4 | 1 | 0 | 0
7.4 | Execute Go-Live | P | 25 | 2027-05-18 | 2027-06-22 | 7.3.6 | 7.4.1 | 25 | 0 | 35
7.4.1 | Prepare go-live checklist | R | 9 | 2027-05-18 | 2027-05-28 | 7.4 | 7.4.2 | 9 | 0 | 10
7.4.2 | Peform pre go-live checks | R | 4 | 2027-05-31 | 2027-06-03 | 7.4.1 | 7.4.3 | 4 | 0 | 3
7.4.3 | Launch System Go-Live | R | 2 | 2027-06-04 | 2027-06-07 | 7.4.2 | 7.4.4 | 2 | 0 | 3
7.4.4 | Monitor system post-launch | R | 4 | 2027-06-08 | 2027-06-11 | 7.4.3 | 7.4.5 | 4 | 0 | 3
7.4.5 | Complete Transition Plan | R | 6 | 2027-06-15 | 2027-06-22 | 7.2.6, 7.4.4 | 7.5 | 6 | 0 | 7
7.5 | Post-Go-Live Support (Hypercare) | P | 13 | 2027-06-23 | 2027-07-09 | 7.4.5 | 7.6 | 13 | 0 | 16
7.6 | Validate and Review Go-Live Success | P | 5 | 2027-07-12 | 2027-07-16 | 7.5 | 7.7 | 5 | 0 | 4
7.7 | Milestone: System Deployed | M | 0 | 2027-07-16 | 2027-07-16 | 7.6 | 8.0 | 0 | 0 | 0
8.0 | Project Closing | O | 24 | 2027-07-19 | 2027-08-19 | 7.7 | 8.1 | 24 | 0 | 31
8.1 | Handover System to TRG IT | P | 7 | 2027-07-19 | 2027-07-27 | 8.0 | 8.1.1 | 7 | 0 | 8
8.1.1 | Prepare Handover Package | R | 7 | 2027-07-19 | 2027-07-27 | 8.1 | 8.2 , 9.1 | 7 | 0 | 8
8.2 | Document Lessons Learnt | P | 15 | 2027-07-28 | 2027-08-17 | 8.1.1 | 8.2.1 | 15 | 0 | 20
8.2.1 | Collect team and stakeholder feedback | R | 4 | 2027-07-28 | 2027-08-02 | 8.2 | 8.2.2 | 4 | 0 | 5
8.2.2 | Consolidate Lessons Learnt | R | 8 | 2027-08-03 | 2027-08-12 | 8.2.1 | 8.2.3 | 8 | 0 | 9
8.2.3 | Share lessons learned with TRG | R | 3 | 2027-08-13 | 2027-08-17 | 8.2.2 | 8.3 | 3 | 0 | 4
8.3 | Archive Project Documentation | P | 2 | 2027-08-18 | 2027-08-19 | 8.2.3 | 8.4 | 2 | 0 | 1
8.4 | Milestone: Project Closure | M | 0 | 2027-08-19 | 2027-08-19 | 8.3 | 9.0 | 0 | 0 | 0
9.0 | Maintenance / Evaluation / Post-Project Support | O | 35 | 2027-08-20 | 2027-10-08 | 8.4 | 9.1 , 9.3 | 35 | 0 | 49
9.1 | Provide Post-Deployment Support | P | 15 | 2027-08-20 | 2027-09-09 | 8.1.1, 9.0 | 9.1.1 | 15 | 0 | 20
9.1.1 | Set up support helpdesk | R | 6 | 2027-08-20 | 2027-08-27 | 9.1 | 9.1.2, 9.1.3 | 6 | 0 | 7
9.1.2 | Provide helpdesk support | R | 4 | 2027-08-30 | 2027-09-02 | 9.1.1 | 9.1.4 | 4 | 0 | 3
9.1.3 | Monitor system issues weekly | R | 4 | 2027-08-30 | 2027-09-02 | 9.1.1 | 9.1.4 | 4 | 0 | 3
9.1.4 | Release minor updates and patches | R | 5 | 2027-09-03 | 2027-09-09 | 9.1.2, 9.1.3 | 9.2 | 5 | 0 | 6
9.2 | Conduct Periodic Reviews and Audits | P | 20 | 2027-09-10 | 2027-10-08 | 9.1.4 | 9.2.1, 9.2.2 | 20 | 0 | 28
9.2.1 | Conduct quarterly performance reviews | R | 10 | 2027-09-10 | 2027-09-23 | 9.2 | 9.2.3 | 10 | 0 | 13
9.2.2 | Conduct quarterly security audits | R | 10 | 2027-09-10 | 2027-09-23 | 9.2 | 9.2.3 | 10 | 0 | 13
9.2.3 | Address and resolve findings in audits | R | 5 | 2027-09-24 | 2027-09-30 | 9.2.1, 9.2.2 | 9.2.4 | 5 | 0 | 6
9.2.4 | Review backup and recovery procedures | R | 5 | 2027-10-01 | 2027-10-08 | 9.2.3 | 9.4 | 5 | 0 | 7
9.3 | Implement Continuous Improvement | P | 20 | 2027-08-20 | 2027-09-16 | 9.0 | 9.3.1 | 20 |  | 27
9.3.1 | Collect user feedback and enhancement requests | R | 4 | 2027-08-20 | 2027-08-25 | 9.3 | 9.3.2 | 4 |  | 5
9.3.2 | Prioritise enhancements roadmap | R | 5 | 2027-08-26 | 2027-09-01 | 9.3.1 | 9.3.3 | 5 |  | 6
9.3.3 | Implement selected enhancements | R | 9 | 2027-09-02 | 2027-09-14 | 9.3.2 | 9.3.4 | 9 |  | 12
9.3.4 | Review enhancement outcomes | R | 2 | 2027-09-15 | 2027-09-16 | 9.3.3 | 9.4 | 2 |  | 1
9.4 | Milestone: Post-Project Review Complete | M | 0 | 2027-10-08 | 2027-10-08 | 9.2.4, 9.3.4 | - | 0 |  | 0
| Total estimated duration (critical path) |  | 418 |  |  |  |  | 418
| Total weeks |  | 86
| End date |  | 2027-10-08
Formulas:
Network days = IF(Gantt4567[[#This Row],[Start]]="","-",NETWORKDAYS(Gantt4567[[#This Row],[Start]],Gantt4567[[#This Row],[End]],Holidays))
Start = [Start, row below]
Start = [Start, row above]
End = IF([Duration (days)]=0,[Start],WORKDAY(Gantt4567[[#This Row],[Start]],Gantt4567[[#This Row],[Duration (days)]]-1,Holidays))
End = IF([Duration (days)]=0,[Start, row above],WORKDAY(Gantt4567[[#This Row],[Start]],Gantt4567[[#This Row],[Duration (days)]]-1,Holidays))
Duration (days) = MAX(D98,MAX([Duration (days), row below],NETWORKDAYS([Start, row below],MAX([End, row below],F88),Holidays))+D93+D102)+D106+D110+D114
Duration (days) = MAX([Duration (days), row below]:D90)+D91+D92+(NETWORKDAYS(E83,MAX(F83,F92),Holidays)-NETWORKDAYS(E83,MAX(F83,F92),Holidays))
Show weekend

## NSW_Holidays
Date | Holiday
2026-01-01 | New Year’s Day
2026-01-26 | Australia Day
2026-04-03 | Good Friday
2026-04-04 | Easter Saturday
2026-04-05 | Easter Sunday
2026-04-06 | Easter Monday
2026-04-25 | Anzac Day | Show weekend | FALSE
2026-06-08 | King’s Birthday | 21
2026-10-05 | Labour Day
2026-12-25 | Christmas Day
2026-12-26 | Boxing Day
2026-12-28 | Additional Day (Substitute)
2027-01-01 | New Year’s Day
2027-01-26 | Australia Day
2027-03-26 | Good Friday
2027-03-27 | Easter Saturday
2027-03-28 | Easter Sunday
2027-03-29 | Easter Monday
2027-04-25 | Anzac Day
2027-06-14 | King’s Birthday
2027-10-04 | Labour Day